CREDIT CARD CHRIS

Launch Campaign Plan

creditcardchris.com  •  Organic Viral Launch  •  Q1 2026

—

| $0 Budget Organic Only | 1–2 Weeks Timeline | Both Audiences Enthusiasts + General | Viral Awareness Primary Goal |
| --- | --- | --- | --- |

# 1. Campaign Overview

## Campaign Name

"Your Card for That" — A viral product launch for Credit Card Chris

## One-Sentence Summary

Show everyday people and points enthusiasts the free app that tells you exactly which credit card to swipe — and turn every early adopter into a word-of-mouth engine.

## Primary Objective

Drive 1,000+ organic signups and 50,000+ impressions within 14 days of launch through community seeding, shareable social content, and referral mechanics — with $0 paid spend.

## Secondary Objectives

- Build an initial community of passionate early adopters on Reddit and social media

- Establish Credit Card Chris as the go-to free tool in the r/churning, r/creditcards, and r/personalfinance communities

- Generate shareable "aha moment" content that spreads naturally (e.g., "I didn't know which card to use for groceries — this app changed that")

- Achieve a notable referral loop: every new user tells at least one friend

# 2. Target Audience

## Primary Audience: Points & Miles Enthusiasts

- Demographics: Ages 22–45, tech-savvy, financially curious

- Psychographics: Obsessed with maximizing rewards, already have 3–6 cards, regularly visit r/churning, r/creditcards, YouTube finance channels

- Pain Points: Forgetting which card earns the most in each category; manually tracking annual fees; no single tool that covers all their cards

- Where they hang out: Reddit (r/churning, r/creditcards, r/personalfinance), Twitter/X finance Twitter, YouTube credit card review channels, Discord servers

- Buying stage: Decision — they want a solution NOW, they just need to find it

## Secondary Audience: Everyday Optimizers

- Demographics: Ages 25–50, have 1–3 credit cards, want to get more from spending but aren't obsessed

- Psychographics: Frugal-minded, budget-aware, motivated by practical savings. They've heard of points but feel overwhelmed

- Pain Points: Don't know which card is best for groceries vs. travel vs. dining; fear missing out on free rewards they're already entitled to

- Where they hang out: TikTok finance content, r/personalfinance, Instagram, Facebook Groups

- Buying stage: Awareness → Consideration — they need a discovery moment

## Key Insight

The viral hook is the same for both audiences: "This is free, and it immediately tells me something I didn't know." The first 30 seconds of using Credit Card Chris should create an "I can't believe I didn't have this" moment.

# 3. Key Messages

## Core Campaign Message

"Stop guessing which card to swipe. Credit Card Chris is the free app that does it for you."

## Supporting Messages by Audience

For Points Enthusiasts

- "Finally — one place to track all 59+ cards and know exactly which earns the most for every category."

- "AI rewards assistant. Ask it anything about your wallet. It actually knows your cards."

- "Transfer partner calculator. Spending insights. Application tracker. Annual fee alerts. All free. Always."

For Everyday Optimizers

- "Set up in 2 minutes. Start earning more on your next grocery run."

- "No bank connections. No data selling. Just smarter spending."

- "The app that tells you: your Amazon card is actually terrible for restaurants. Use the blue one instead."

## Proof Points

- 59+ cards supported across 20+ issuers — the broadest free coverage available

- Free forever — no premium tier, no upsells, no "pro" lock

- Privacy-first — no bank logins, no financial data sold, ever

- AI assistant trained on YOUR wallet, not generic advice

- PWA — works on mobile without an app store download

# 4. Channel Strategy

With a $0 budget, every channel must earn attention through genuine value. The strategy is: seed credibility in niche communities first, then let social amplification do the work.

| Channel | Why It Fits | Content Format | Effort |
| --- | --- | --- | --- |
| Reddit (r/churning, r/creditcards, r/personalfinance) | 21M+ members in PF alone. Highest intent audience for a rewards optimizer. Trust-driven community where genuine tools get organic traction. | Authentic launch post, AMA, comment-first strategy (15–25 helpful comments before posting) | High |
| TikTok / Reels | 49% of Gen Z uses TikTok as a search engine. Short 'swipe hack' videos get explosive reach. Finance content is booming. | 7–20 sec screen recordings: 'Which card for X?' demo videos, 'I found a free app that...' hooks | Medium |
| Twitter / X (FinTwit) | Credit card Twitter is active and vocal. A single well-crafted thread can drive thousands of signups from engaged followers. | Launch thread, reply to relevant conversations, screenshot-worthy stats (e.g., 'I was leaving $400/yr on the table') | Medium |
| Product Hunt | The go-to platform for app launches. #1 Product of the Day drives thousands of genuine signups from tech-forward users. | Full product listing with demo GIFs, genuine description, upvote campaign from personal networks | High (one day) |
| Email / Referral (Word of Mouth) | Every early adopter becomes a distribution channel. A simple 'share with a friend' nudge inside the app multiplies organic reach. | In-app share prompt after first 'aha moment', shareable card wallet summary screenshots | Low |
| Hacker News (Show HN) | Tech-savvy audience, high Google SEO value for 'Show HN' posts. Can drive hundreds of signups and press attention. | 'Show HN: I built a free credit card rewards optimizer' — leads to viral developer/tech audience pickup | Low–Medium |

# 5. Content Calendar

14-day sprint. Week 1 = community seeding + launch. Week 2 = amplification + momentum.

## Pre-Launch (Days 1–3): Build Credibility

| Day | Action | Channel | Notes |
| --- | --- | --- | --- |
| Day 1 | Comment on 5 top posts in r/churning and r/creditcards with genuinely useful advice (no links) | Reddit | Build karma; understand current community questions |
| Day 1 | Comment on 5 posts in r/personalfinance about card optimization questions | Reddit | Same — add value only |
| Day 2 | Comment on 10 more Reddit posts. Identify the top pain points being discussed. | Reddit | This is research + trust building |
| Day 2 | Shoot 2–3 TikTok/Reels screen recording demos: 'Best card for groceries' and 'How I track my annual fees' | TikTok / Reels | Don't name the app yet — just show the concept. Hook them first. |
| Day 3 | Draft Reddit launch post. Draft Product Hunt listing. Set Product Hunt launch date for Day 5. | Reddit / PH | Write like a founder, not a marketer. Tell the story. |
| Day 3 | Post TikTok #1 — framing the PROBLEM: 'Do you know which card earns the most on Amazon?' | TikTok | Zero product mention. Just the hook. |

## Launch Week (Days 4–7): Go Live

| Day | Action | Channel | Notes |
| --- | --- | --- | --- |
| Day 4 | Post 'Show HN: I built a free credit card rewards optimizer — which card to swipe for every purchase' | Hacker News | Submit between 10am–12pm ET for max visibility. Link to creditcardchris.com directly. |
| Day 5 | Reddit launch post in r/creditcards: 'I built a free app to tell you which credit card to use for every purchase (59+ cards supported)' | Reddit | Be transparent as founder. Lead with what it DOES. Include 1 screenshot. Respond to EVERY comment same day. |
| Day 5 | Product Hunt launch — ask friends/community to upvote and leave honest reviews | Product Hunt | Aim for Top 5 of the day. Post at midnight PST. |
| Day 5 | TikTok #2 — SOLUTION reveal: 'Found a free app that tells you exactly which card to swipe' | TikTok | Screen record the app. Show the 'best card for groceries' recommendation. CTA: 'Link in bio'. |
| Day 6 | Cross-post to r/personalfinance: 'I made a free tool to stop leaving rewards on the table' | Reddit | Tailor the post for the PF audience — emphasize savings and simplicity over points hacking |
| Day 6 | Twitter/X launch thread: 'I built a free credit card rewards optimizer. Here's what I learned about how much money people leave on the table every year 🧵' | Twitter/X | 7–10 tweet thread. Include real stats, app screenshots, and a clear CTA at the end. |
| Day 7 | TikTok #3 — testimonial/reaction: 'I didn't realize my cashback card was the worst choice for restaurants' | TikTok | Use your own data as an example. Real discovery moments = viral content. |

## Amplification Week (Days 8–14): Momentum

| Day | Action | Channel | Notes |
| --- | --- | --- | --- |
| Day 8–9 | Respond to all comments, DMs, and feedback from launch. Answer questions thoroughly. | All | Community trust = word of mouth. Don't ghost your first users. |
| Day 8 | Post to r/frugal: 'Free tool I made to stop leaving free rewards on the table' | Reddit | Third subreddit. Frugal audience cares deeply about optimization. |
| Day 9 | TikTok #4 — 'How I set up my credit card wallet in 2 minutes' walkthrough | TikTok | Reduce friction. Show how easy signup is. |
| Day 10 | Reach out to 3–5 small credit card YouTube creators / personal finance TikTok creators for organic features | DM Outreach | Not paid. Just 'I built this free tool — want to check it out?' Personalize each message. |
| Day 11 | Post in r/digitalnomad, r/solotravel, or travel communities: 'Free app to maximize travel credit cards' | Reddit | Expand to adjacent communities with high card interest. |
| Day 12 | TikTok #5 — 'The credit cards I use for every spending category (powered by CreditCardChris.com)' | TikTok | Personal wallet reveal = very shareable format in FinTok. |
| Day 14 | Week 2 retrospective Reddit post: 'Update: X users, top questions we've answered, what's next' | Reddit | Transparency builds loyalty. Share real numbers if positive. Ask for feedback. |

# 6. Content Assets Needed

| Asset | Description | Priority | Due |
| --- | --- | --- | --- |
| Reddit Launch Post (r/creditcards) | Authentic founder post: what the app does, why it's free, screenshot of best card recommendation UI. 300–500 words. | Must-have | Day 4 |
| Reddit Post (r/personalfinance) | Reframed for savings-focused audience. Emphasize: 'stop leaving free money behind.' Different angle from r/creditcards post. | Must-have | Day 5 |
| Show HN Post | Technical, honest, short. 'I built X, here's the stack, here's the problem I solved.' Link to live site. | Must-have | Day 4 |
| Product Hunt Listing | Title, tagline, description, 3–5 screenshots, GIF walkthrough of key feature (best card picker). Tagline should be punchy. | Must-have | Day 4 |
| Twitter/X Launch Thread | 7–10 tweets. Hook tweet with a stat or question. Problem → Solution → Demo → CTA. Include 2 screenshots. | Must-have | Day 6 |
| TikTok #1 — Problem Hook | Short, no product. 'Do you actually know which card earns the most on groceries?' Ends on a cliffhanger. | Must-have | Day 3 |
| TikTok #2 — Solution Reveal | Screen recording of app. Best card for category recommendation. 'Found a free app that tells you this instantly.' | Must-have | Day 5 |
| TikTok #3 — Personal Discovery | Real 'aha moment' using your own data. 'I was using the wrong card for restaurants for 2 years.' | Must-have | Day 7 |
| TikTok #4 — Onboarding Walkthrough | 2-minute setup screen recording. Show the speed and simplicity. | Must-have | Day 9 |
| TikTok #5 — Wallet Reveal | 'My full credit card stack and which I use for what' — personal, shareable format | Must-have | Day 12 |
| In-App Share Prompt | After first recommendation, show: 'Know someone with credit cards? Share Credit Card Chris.' Include shareable image/link. | Must-have | Pre-launch |
| Reddit Post (r/frugal) | Third community post. Short, practical: 'built a free tool to squeeze more value from cards you already have.' | Nice-to-have | Day 8 |
| Outreach Message (Creators) | Personalized DM template for TikTok/YouTube creators. Casual, not promotional. Include your Product Hunt link. | Nice-to-have | Day 10 |
| Week 2 Update Post | Transparent retrospective: user count, top feedback, what's coming next. Keep the community warm. | Nice-to-have | Day 14 |

# 7. Success Metrics

| Metric | Target (14 days) | How to Track |
| --- | --- | --- |
| New Signups | 1,000+ accounts created | Supabase auth — count new users created in 14-day window |
| Total Impressions | 50,000+ across all channels | Reddit post views + TikTok views + Twitter impressions |
| Reddit Post Upvotes | 200+ combined across all posts | Reddit post analytics |
| TikTok Views | 10,000+ across 5 videos | TikTok creator analytics |
| Product Hunt Rank | Top 5 Product of the Day | Product Hunt dashboard |
| Referral Rate | 20%+ of new users via word-of-mouth | Add UTM params to social links; track referral source in Supabase |
| Day 7 Retention | 30%+ of Day 1 signups return by Day 7 | Supabase — query users who logged in on Day 1 AND Day 7 |
| App 'Aha Moment' Rate | 70%+ of signups add at least 1 card | Supabase — count users who added ≥1 card within 24hr of signup |

## Reporting Cadence

- Daily: Check signup count, Reddit upvotes, TikTok views

- Day 7: Mid-launch review. Double down on what's working. Kill what isn't.

- Day 14: Full retrospective — what drove signups, top retention source, community sentiment

# 8. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Reddit posts get removed as self-promotion | High (if done wrong) | Comment 15–25 times BEFORE posting. Always disclose you're the founder. Lead with value, not a link. Read each subreddit's rules before posting. |
| TikTok videos get low reach on launch | Medium | Post at peak times (Tue–Fri, 7–9am or 7–9pm local). Use trending audio. First 3 seconds must hook — rewrite if the first video flops. |
| Signups don't convert to active users | Medium | Ensure the onboarding is frictionless and the first 'best card' recommendation is instant and surprising. The aha moment must happen within 2 minutes of signup. |
| No viral moment emerges in Week 1 | Low–Medium | Have 2 'hero content' pieces ready (the best TikTok and the Reddit post). If neither gains traction, pivot to smaller subreddits (r/frugal, r/solotravel, r/digitalnomad) and niche creator outreach. |

# 9. Next Steps

Start today. The launch window is now. Here's your immediate action list:

- Add UTM tracking to all links (Reddit, TikTok bio, Product Hunt) so you know which channel drives signups

- Add an in-app share prompt that fires after a user gets their first card recommendation

- Create your Reddit account if new, or age it by commenting on r/churning and r/creditcards today

- Film TikTok #1 (problem-only hook video) and schedule for Day 3

- Register and draft your Product Hunt listing — schedule the launch for Day 5

- Draft your Reddit launch post with founder voice, 1 screenshot, and honest CTA

- Write your Twitter/X launch thread — save as draft, ready to post Day 6

The single most important thing you can do right now:

Make sure the first 2 minutes of using Credit Card Chris creates a genuine 'I didn't know that' moment. Every campaign tactic above amplifies that reaction. Without it, no amount of marketing will drive word-of-mouth.

Prepared for Credit Card Chris • creditcardchris.com • March 2026