CREDIT CARD CHRIS

Paid Launch Campaign Plan

creditcardchris.com  •  $100–$500 Budget  •  Q1 2026

—

| $100–$500 Total Budget | 1–2 Weeks Timeline | Both Audiences Enthusiasts + General | Viral Awareness Primary Goal |
| --- | --- | --- | --- |

# 1. Campaign Overview

## Campaign Name

"Swipe Smarter" — A paid + organic launch for Credit Card Chris

## One-Sentence Summary

Combine targeted paid distribution with organic community seeding to drive mass awareness of the free rewards optimizer — using budget to amplify the content that earns attention on its own first.

## How This Differs from the $0 Plan

The $0 plan relies entirely on organic reach. This plan uses budget to amplify what's already working: boost a TikTok video after it gets 500+ organic views, run Reddit Ads targeting r/churning and r/creditcards, and pay micro-influencers $50–100 each to do a genuine first-use reaction. Organic content still leads — paid is the accelerant.

## Primary Objective

Drive 3,000–5,000 signups and 150,000+ total impressions within 14 days through a blend of targeted paid ads, micro-influencer seedings, and organic community posts — with a $100–$500 spend cap.

## Secondary Objectives

- Achieve a cost-per-signup (CPS) under $0.15 — proving paid is viable before scaling further

- Identify the single highest-converting content format (TikTok vs. Reddit Ad vs. influencer) for future campaigns

- Build an email list of 500+ engaged early adopters for a retention loop

- Rank in Top 3 on Product Hunt on launch day

# 2. Budget Allocation

Three scenarios: lean ($100), core ($250), and full ($500). Spend in order — validate before scaling.

| Channel / Activity | Lean ($100) | Core ($250) | Full ($500) | Notes |
| --- | --- | --- | --- | --- |
| TikTok / Instagram Reels Boost | $40 | $80 | $120 | Boost the best-performing organic video after 500+ organic views. $10/day × 4–12 days. Target: US, ages 22–45, interests in finance/travel. |
| Reddit Ads (r/creditcards, r/churning, r/personalfinance) | $40 | $100 | $160 | Promoted post format (looks native). Target specific subreddits. CPC typically $0.50–1.50 in finance. CPM ~$6–12. |
| Micro-Influencer Seedings (TikTok / YouTube Shorts) | $0 | $50 | $150 | Pay 1–3 personal finance micro-creators ($50–100 each) for a genuine first-use review. Look for 5k–50k followers with high engagement. |
| Product Hunt Sponsored Featured | $0 | $0 | $50 | Optional: PH featured placement on launch day. Not always worth it — organic upvote momentum matters more. |
| Twitter/X Paid Promotion | $0 | $20 | $20 | Promote your launch thread to followers of @ThePointsGuy, @NerdWallet. Small budget, useful for FinTwit reach. |
| Contingency / Testing Buffer | $20 | $0 | $0 | Hold back $20 to double down on whatever performs best in first 3 days. |
| TOTAL | $100 | $250 | $500 | Spend in order. Validate CPS at each tier before advancing. |

Key Rule: Never boost content before it's proven. Post organically first. Wait for 500+ organic views on TikTok or 50+ upvotes on Reddit before spending $1 to amplify it. Paid budget should accelerate winners — not prop up losers.

# 3. Target Audience

## Paid Targeting Specs

TikTok / Reels Ad Targeting

| Parameter | Setting |
| --- | --- |
| Age | 22–45 |
| Location | United States (English-speaking) |
| Interests | Personal Finance, Travel Rewards, Credit Cards, Points & Miles, Cashback |
| Behavior | Users who engage with financial content, frequent online shoppers |
| Exclude | Users who have already visited creditcardchris.com (custom audience via pixel) |
| Ad Format | In-feed video (9:16). Use best organic TikTok as creative — no polished ad feel. |

Reddit Ads Targeting

| Parameter | Setting |
| --- | --- |
| Communities | r/creditcards, r/churning, r/personalfinance, r/frugal, r/solotravel |
| Ad Format | Promoted Post (native-looking). Use headline: 'Free app that tells you which credit card to swipe — 59 cards supported' |
| Bidding | CPC (cost-per-click). Set max bid $1.00. Start with $10/day. |
| Creative | Single image: screenshot of the 'best card for category' UI. Clean, no marketing fluff. |
| Exclude | Existing website visitors via Reddit Pixel |

Micro-Influencer Criteria (Core + Full Budget)

- Follower count: 5,000–100,000 (micro — high engagement rate, lower cost)

- Content niche: personal finance, credit cards, travel hacking, or 'money tips'

- Engagement rate: 3%+ (likes + comments / followers)

- Platform: TikTok-first (highest viral coefficient), YouTube Shorts second

- Deliverable: 1 organic-looking first-use reaction video. No scripts — just genuine use

- Cost: $50–$150 per creator. Always negotiate for usage rights.

# 4. Channel Strategy

Organic channels from the $0 plan remain the foundation. Budget channels amplify them.

| Channel | Role in This Plan | Budget Tier | Expected Output |
| --- | --- | --- | --- |
| Reddit (Organic) | Credibility + community trust. Foundation of launch. | Free | 200+ upvotes, 1,000+ signups from r/creditcards post |
| Reddit Ads | Paid amplification of best organic post to wider subreddit audiences. | Core ($100) / Full ($160) | 5,000–15,000 impressions, est. 200–600 clicks @ $0.50–1.00 CPC |
| TikTok (Organic) | Viral awareness engine. Problem-hook videos first. | Free | 10,000–30,000 organic views across 5 videos |
| TikTok Boost | Amplify best-performing video after organic validation. | Lean ($40) / Full ($120) | 50,000–150,000 additional impressions, est. 500–2,000 profile visits |
| Micro-Influencers | Trusted third-party credibility. 'A creator I follow showed me this app' drives the highest-converting traffic. | Core ($50) / Full ($150) | 1–3 videos, est. 20,000–80,000 views, high trust conversion |
| Product Hunt | Single-day spike. Top 3 = homepage feature = thousands of organic signups. | Free (+ optional $50) | 500–2,000 signups on launch day if Top 5 |
| Show HN | Tech audience, SEO value, credibility. | Free | 200–800 signups |
| Twitter/X Thread | FinTwit reach. Promoted version targets followers of major finance accounts. | Free + optional $20 | 5,000–20,000 impressions on thread |
| Email Capture | Every signup should enter a lightweight nurture sequence (2–3 emails). Turns curiosity into retained users. | Free | 500+ email list by Day 14 |

# 5. Content Calendar

Same 14-day structure as the organic plan, with paid amplification layered in after organic validation on Days 3–5.

## Pre-Launch (Days 1–3): Seed + Create

| Day | Action | Channel | Spend | Notes |
| --- | --- | --- | --- | --- |
| Day 1 | Comment on 20+ posts in r/churning, r/creditcards, r/personalfinance | Reddit | $0 | Build karma. Disclose you're a builder. Never link yet. |
| Day 1 | Identify 5–10 micro-influencer candidates on TikTok/YouTube | Research | $0 | DM 5 today: 'I built a free tool, want to check it out before launch?' |
| Day 2 | Film TikTok #1 — problem hook: 'Do you know which card earns the most at Whole Foods?' | TikTok | $0 | Post organically. No product mention. Watch 24hr performance. |
| Day 2 | Set up Reddit Ads account. Create campaign targeting r/creditcards — paused. | Reddit Ads | $0 (setup) | Don't activate until launch. Have creative ready. |
| Day 3 | TikTok #1 hits 500+ views? Start $10/day boost. | TikTok Boost | $10–30 | If under 500 views, don't boost. Try different hook instead. |
| Day 3 | Film TikTok #2 — solution reveal with app screen recording | TikTok | $0 | Post organically Day 4. |
| Day 3 | Finalize Product Hunt listing. Schedule for Day 5 midnight PST. | Product Hunt | $0 | Gather 10–15 friends/beta users ready to upvote at launch. |

## Launch Week (Days 4–7): Go Live + Amplify

| Day | Action | Channel | Spend | Notes |
| --- | --- | --- | --- | --- |
| Day 4 | Post: 'Show HN: I built a free app that tells you which credit card to use for every purchase' | Hacker News | $0 | 10am ET. Drives tech signups + SEO. |
| Day 4 | Activate Reddit Ads campaign — r/creditcards and r/personalfinance. $10/day. | Reddit Ads | $10/day | Use the best screenshot from the app. Headline: 'Free app: which card earns the most for your purchase category?' |
| Day 5 | Reddit launch post: r/creditcards — founder story, genuine reveal, 1 screenshot. | Reddit | $0 | Respond to every comment within 2 hours. This is your highest-ROI action of the 14 days. |
| Day 5 | Product Hunt goes live at midnight PST. | Product Hunt | $0 or $50 | Alert your network. Respond to every comment on PH. |
| Day 5 | TikTok #2 — solution reveal video posted. | TikTok | $0 | Boost if it hits 500 views within 6 hours. |
| Day 6 | Cross-post to r/personalfinance | Reddit | $0 | Rewrite for savings/frugal angle. Different headline. |
| Day 6 | Twitter/X launch thread. Pin to profile. | Twitter/X | $0 or $20 | 7–10 tweets. Include PH link + CTA. Promote tweet if budget allows. |
| Day 7 | TikTok #3 — 'I was using the wrong card for 2 years' personal discovery story. | TikTok | $0 | Boost if organic traction is strong. |
| Day 7 | Check influencer responses. Confirm 1–2 creators will post next week. | Influencer | $50–150 | Send app access + brief: 'Just be honest. Show first use.' |

## Amplification Week (Days 8–14): Double Down

| Day | Action | Channel | Spend | Notes |
| --- | --- | --- | --- | --- |
| Day 8 | Review Day 4–7 data. Kill Reddit Ad if CPC > $1.50. Reallocate to TikTok boost. | Analysis | $0 | Budget reallocation decision point. Follow the data. |
| Day 8–10 | Micro-influencer videos go live. Engage with their comments. | Influencer | $50–150 | Comment on their post as the founder: 'This is my app — happy to answer any questions!' DM interested commenters. |
| Day 9 | TikTok #4 — onboarding walkthrough: '2-minute setup, then it tells you everything' | TikTok | $0–$30 boost | Boost if previous videos performing well. |
| Day 10 | Post to r/frugal — 'Free tool to squeeze more from the cards you already have' | Reddit | $0 | Third subreddit. Different angle again. |
| Day 11 | Email to all signups: 'Here's what your wallet is telling us...' — personalized insight email. | Email | $0 | Use Supabase data to pull a real insight. Show them something they didn't know. Drives D7 retention. |
| Day 12 | TikTok #5 — 'My full credit card wallet reveal powered by creditcardchris.com' | TikTok | $0–$30 boost | Personal, shareable. Name the app clearly. |
| Day 14 | Turn off Reddit Ads. Final budget check. Write retrospective Reddit post: 'X signups in 14 days — here's what happened' | Reddit | End spend | Transparency = trust. Share real numbers. Ask for feedback. |

# 6. Content Assets Needed

All assets from the $0 plan, plus these additional paid-specific assets:

| Asset | Description | Priority | Due | Budget |
| --- | --- | --- | --- | --- |
| Reddit Ad Creative (Image) | Clean screenshot of the 'best card for category' UI with minimal text overlay. No corporate polish — looks like an organic post screenshot. | Must-have | Day 3 | $0 (DIY) |
| Reddit Ad Headline Copy (3 variants) | A/B test 3 headlines: (1) 'Free app: which card earns the most for every purchase?', (2) 'Stop guessing which card to swipe — 59 cards supported', (3) 'I built a free credit card optimizer — r/creditcards helped shape it' | Must-have | Day 3 | $0 |
| TikTok Ad Creative | Use best organic TikTok as boost creative. No new production needed — just boost what works. | Must-have | Day 3–5 | $40–120 |
| Influencer Brief (1 page) | One-page PDF: what the app does, the 3 features to highlight, what NOT to say (no 'ad-speak'), link, promo code if applicable. | Must-have | Day 6 | $0 (write yourself) |
| Onboarding Email #1 | 'Welcome to Credit Card Chris — here's your first insight.' Personalized with their card data if available. Drives D1 retention. | Must-have | Pre-launch | $0 |
| Onboarding Email #2 (Day 3) | 'Did you know your [card] is the worst for [category]?' — surfaces a genuine aha moment from their wallet. | Must-have | Pre-launch | $0 |
| UTM Link Set | Unique UTM parameters for every channel: reddit-organic, reddit-ad, tiktok-organic, tiktok-boost, influencer-[name], producthunt, hackernews. Critical for budget ROI tracking. | Must-have | Day 1 | $0 |
| Product Hunt GIF Walkthrough | 15-sec screen recording showing: add card → get best card recommendation → AI chat. Used in PH listing. | Must-have | Day 4 | $0 (Loom or QuickTime) |
| Twitter/X Promoted Tweet Creative | The hook tweet from the launch thread. Must work without seeing the rest of the thread. | Nice-to-have | Day 6 | $20 |

# 7. Success Metrics

| Metric | Target (14 days) | How to Track | Budget Tier |
| --- | --- | --- | --- |
| New Signups | 3,000–5,000 | Supabase auth — new users in 14-day window | All |
| Cost Per Signup (CPS) | Under $0.15 | Total paid spend ÷ signups attributed to paid channels via UTM | Lean+ |
| Total Impressions | 150,000+ | Reddit Ads dashboard + TikTok analytics + influencer view count | All |
| Reddit Ad CTR | 0.3–0.8% | Reddit Ads campaign manager | Core+ |
| TikTok Boost ROAS | 500+ profile visits per $40 spent | TikTok Ads Manager | Lean+ |
| Influencer Video Views | 20,000+ per creator | Creator shares screenshot on Day 7 | Core+ |
| Product Hunt Rank | Top 3 of the Day | Product Hunt dashboard | All |
| Day 7 Retention | 35%+ return rate | Supabase query: users active on Day 1 + Day 7 | All |
| Email List Size | 500+ | Email provider (Resend/Postmark/Mailchimp) | All |
| Onboarding Completion | 60%+ add first card | Supabase — users with ≥1 card within 24hr of signup | All |

## The Key Paid Metric to Watch

Cost Per Signup (CPS). If Reddit Ads are delivering CPS > $0.25, pause them and reallocate to TikTok boost. If TikTok boost is delivering CPS < $0.05, increase budget. Measure CPS every 48 hours and shift budget to the winner.

# 8. Budget Scenarios

## Scenario A: Lean ($100)

| Channel | Spend | Expected Signups |
| --- | --- | --- |
| TikTok Boost (best organic video) | $40 | 150–400 |
| Reddit Ads (r/creditcards) | $40 | 80–200 |
| Contingency / reallocation | $20 | — |
| TOTAL | $100 | 230–600 paid-attributed |

## Scenario B: Core ($250)

| Channel | Spend | Expected Signups |
| --- | --- | --- |
| TikTok Boost | $80 | 300–700 |
| Reddit Ads (2 subreddits) | $100 | 200–500 |
| 1 Micro-influencer ($50) | $50 | 200–600 (high trust = high conversion) |
| Twitter/X Promotion | $20 | 50–150 |
| TOTAL | $250 | 750–1,950 paid-attributed |

## Scenario C: Full ($500)

| Channel | Spend | Expected Signups |
| --- | --- | --- |
| TikTok Boost (2 videos) | $120 | 500–1,200 |
| Reddit Ads (3 subreddits) | $160 | 400–900 |
| 2–3 Micro-influencers | $150 | 500–1,500 |
| Twitter/X Promotion | $20 | 50–150 |
| Product Hunt Featured | $50 | 100–300 |
| TOTAL | $500 | 1,550–4,050 paid-attributed |

Recommendation: Start with Scenario A ($100) for the first 7 days. If CPS is under $0.10, immediately deploy an additional $150 (Scenario B delta). If still strong, add the remaining $250. Don't commit the full $500 upfront — validate first.

# 9. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Reddit Ads flagged as spam or low CTR | Medium | Use 'Promoted Post' format (native-looking). Lead with community value, not a sales pitch. Test 3 headline variants — kill the worst after 48 hours. |
| Influencer posts don't convert | Medium | Vet creators by engagement rate, not follower count. Send product access 3 days before asking for a post. Only pay after the video is live and approved. Ask for 'link in bio' CTA. |
| TikTok boost spends budget with low click-through | Low–Medium | Only boost a video that has 3%+ engagement rate organically. If CPM is high but CTR is below 1%, swap the creative. |
| Budget runs out before Day 14 | Low | Day 7 checkpoint: if paid CPS is above $0.20, pause all paid spend and return to organic-only for the second week. |
| Signups don't convert to active users even with paid traffic | Medium | This means the onboarding, not the marketing, is the problem. If retention is below 25%, pause paid spend and fix the first-use experience before spending more. |

# 10. Next Steps

Do these today. Launch in 3 days.

- Set up UTM parameters for ALL channels (create a simple UTM builder spreadsheet)

- Install Reddit Pixel and TikTok Pixel on creditcardchris.com for retargeting + conversion tracking

- Create Reddit Ads account and build the campaign — targeting r/creditcards — but leave it paused

- Film and post TikTok #1 (problem hook). Watch performance for 24 hours. If 500+ views, boost.

- DM 5–10 micro-influencer candidates today. Keep it casual and genuine.

- Write 2-email onboarding sequence and load into your email tool (Resend, Mailchimp, etc.)

- Schedule Product Hunt launch for Day 5 at midnight PST. Recruit 15+ first upvoters now.

- Set a Day 7 budget checkpoint reminder: review CPS and reallocate or kill paid spend based on data

The difference between the $0 and $500 plan isn't $500 worth of signups — it's the data. By Day 7 you'll know exactly which channel drives the best users at the lowest cost. That knowledge is worth far more than the signups themselves.

Prepared for Credit Card Chris  •  creditcardchris.com  •  March 2026